## Sheet1
Gantt Chart for the Sumersible Pump Impeller Defect Detection Application Project
Task Description | 11th March 2024 | 18th March 2024 | 25th March 2024 | 1st April 2024 | 8th April 2024 | 15th April 2024 | 22nd April 2024 | 29th April 2024 | 6th May 2024
Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Total
Development of a Gnatt Chart | 2 | [8 empty] | 2
Writing acceptance criteria and users story | 4 | [8 empty] | 4
Aglorithm Development using Jupyter notebook |  | 7 | 7 | 8 | [5 empty] | 22
Saving and Developing the Best ML model in Jupyter |  |  |  | 7 | [5 empty] | 7
Creation of a Streamlit app |  |  |  |  | 6 | 8 |  |  |  | 14
Testing and Evaluating the Project | [6 empty] | 6 | 4 |  | 10
Deploying the Product for use | [7 empty] | 7 | 3 | 10
Total Hours Per Week | 6 | 7 | 7 | 15 | 6 | 8 | 6 | 11 | 3 | 69
Non-Critical Task
Critical Task